## Sheet1
Misamis Occidental I Electric Cooperative, Inc.
Magcamiguing, Calamba, Misamis Occidental
(Tel No. 088-271-3661; Email Address: moelci_uno@moelci-1.com)
MATRIX OF BIDDING ACTIVITIES
PROJECT TITLE |  | SUPPLY AND DELIVERY OF VARIOUS SIZES, DISTRIBUTION TRANSFORMERS
Approved Budget of Contract |  | 12132000 |  |  |  | BID PRICE | 6900000
Procurement Activity |  | Minimum Calendar Days | Maximum Calendar Days | Actual Schedule | No. of Days
1 | Pre-Procurement Conference |  |  | 2026-06-11
| BOD Approval of BID Documents |  |  | 2026-06-26
2 | Advertisement/Posting of Invitation to BID | (Day 1-7) | Day 1-7 | 2026-07-02
3 | Pre BID Conference | (Day 8) | Day 8-40 | 2026-07-10 | 8 | PIURCHASED BIDDING DOCS. | AISON | 10/24/2025
4 | Deadline of Submission and Receipt of BIDS | (Day 20) | Day 52 | 2026-07-22 | 20
| BID Opening | (Day 20) | Day 52 | 2026-07-22 | 20
5 | BID Evaluation | (Day 21) | Day 53-59 | 2026-07-23 | 21
6 | Post Qualification | (Day 22-23) | Day 60-104 | 2026-07-27 | 25 | BAC RESOLUTION | NO. 6,s.2026 | 2026-09-01
7 | Approval of Resolution | (Day 24) | Day 105-119 | 2026-08-07 | 36
| Issuance of Notice of Award | (Day 24) | Day 105-119 | 2026-08-07 | 36
8 | Contract Preparation and Signing | (Day 25) | Day 120-129 | 2026-08-17 | 46
9 | Approval of Contract by Higher Authority |  |  | 2026-08-27 | 56
10 | Issuance of Notice to Proceed | (Day 26) | Day 130-136 | 2026-08-27 | 56
| TOTAL TIME: | 26 CDs | 136 CDs | 56
REMARKS:
Prepared by:
PERCIVAL M. GUMELA
Chairman, Bids and Awards Committee/Area Office Department Manager
Formulas:
Actual Schedule = [Actual Schedule, row above]+8